## Slide 1: ISA2: 2016.16 - Public Multilingual Knowledge Management Infrastructure for the Digital Single Market(PMKI)

## Slide 2: Agenda
PMKI project
  Context, Objectives, Organisation
  Use cases
PMKI requirements
  Solution architecture
  Status in 2019
Semantic alignment and interoperability in PMKI
Conclusions

## Slide 3: PMKI organisation
Type of activity | Common services, common frameworks (Creation of a Public Multilingual Knowledge Infrastructure (PMKI))
Service in charge | Publications Office of the European Union OP.A2
Associated Services | CNECT.G3 DIGIT.D2 DGT.R3 European Parliament, DG TRAD, Terminology Coordination unit
First approval of the proposal by the ISA² committee | March 2nd 2016 in the scope of the general presentation of the ISA² programme
Timeframe | 2016 –2019

## Slide 4: Context
Digital Single Market (DSM) for Europe (priority of Junker's Commission)
  Bringing down barriers, including language barriers
    Only 7% of SMEs in the EU are actually selling cross-border
  Unlock on-line, cross-border opportunities
    EU cross-border on-line services represent only 4% of the global Digital Market
"Overcoming language barriers is vital for building the DSM, which is by definition multilingual"
Blog post by Commissioner Andrus Ansip at the 27 May 2016
Contribution of PMKI:
  Interoperability Platform for language resources (vocabularies, thesauri) reusable for the aim of creating a Multilingual Digital Single Market.

## Slide 5: Objectives of the PMKI project
To create a proof-of-concept for a public multilingual knowledge infrastructure enabling interoperability between multilingual terminologies.
To propose a common data model for multilingual terminologies based on existing recognised standards.
To develop semantic capabilities enabling the automated alignment of data from different sources in order to further increase their interoperability.

## Slide 6: Positioning of PMKI in the common architecture for the multilingual DSM promoted by the EU Language Technology industry
Context

## Slide 7: Use-cases, overview
Multilingual search
… as support for cross-lingual information retrieval solutions
(index and/or query extension)
Localisation
… as support for systems that deal
with the localisation of Websites
Machine translation: …as support for machine translation systems (to increase quality)

## Slide 8: Connection with computer-assisted translation (CAT) tool

## Slide 9: Solution, PMKI Architecture
Users
KNOWLEDGE BASE
Concepts, relations
ACCESS
SPARQL endpoint, RESTful API
KNOWLEDGE MODEL
Core data model (Ontolex-Lemon)
SERVICES
Ingestion, alignment, data and knowledge model management, publishing, conversion, administration of the platform

## Slide 10: Access
PMKI Requirements
  Visualisation and browsing
    terms, concepts, relations, metadata and statistics
  Graphical visualisations of concepts and terms and their relations
  Search & Retrieval
    full-text search over the content of the public knowledge base (including metadata)
  RESTful API and SPARQL endpoint
    resources available in different RDF serialization formats (SKOS, SKOS-XL, OntoLex-Lemon).

## Slide 11: Knowledge Base
PMKI Requirements
  Language and semantic resource repository according to Semantic Web and Linked Open Data principles
  Automatic alignment facilities

## Slide 12: Knowledge Model
PMKI requirements
  based on existing standards (Ontolex-Lemon)
  reviewed by external experts

## Slide 13: Back-offices Services
PMKI Requirements
  managing data and knowledge models
  supporting Ontolex-Lemon on top of RDFS, OWL, SKOS and SKOS-XL

## Slide 14: Common approach for PMKI and VocBench
Back-end layer (Vocbench 3 for PMKI)
    Knowledge Base (staging area )
    Knowledge Model
Front-end layer (Dissemination platform for PMKI)
    Knowledge Base (public)
    Access Services
  Activities started end 2018

## Slide 15: Publishing and conversion services
PMKI Requirements
  publishing service for uploading/updating language resources
  back-office staging area and dissemination area
  conversion service
    TBX to Ontolex-Lemon for lexicons;
    zThes to SKOS for thesauri;
    Spreadsheet format to SKOS for thesauri.
  accessible by registered users

## Slide 16: Current status: milestones
ISA2 request 2019 |  |  | Workplan |  | 
Phase | Description of milestones reached or to be reached | Start date End date | Start date End date | Status | % Comp.
Inception | Project organisation has been set-up | Q3/16-Q4/16 | Q3/16-Q4/16 | Done | 100%
Execution | Standard representation has been adopted | Q4/16-Q1/17 | Q4/16-Q1/17 | Done | 100%
Execution | Core data model and a first set of extensions have been defined (including documentation) | Q4/16-Q4/17 | Q4/16-Q4/17 | Done | 100%
Execution | Technical architecture has been defined | Q2/17-Q1/18 | Q2/17-Q3/17 | Done | 100%
Execution | Proposal for an adequate governance structure has been defined | Q1/17-Q3/17 | Q2/17-Q3/17 | Done | 100%
Execution | First release of the system | Q3/18-Q1/19 | Q3/18-Q3/19 | Ongoing | 80%
 | Operational prototype | Q1/19-Q2/19 | Q3/19-Q4/19 | Planned | 
Execution | Proposal for the implementation strategy | Q1/19-Q4/19 | Q1/19-Q4/19 | Planned | 
Execution | Creation of the community | Q4/18-Q4/19 | Q4/18-Q4/19 | Ongoing | 70%
Execution | Feasibility study for the enhancement of the semantic capabilities of the platform | Q3/17-Q4/18 | Q3/17-Q4/18 | Done | 100%
Execution | Project management support | Q1/18-Q4/19 | Q1/18-Q4/19 | Ongoing | 70%
 | Total |  |  |  | 

## Slide 17
Semantic Alignment in PMKI
Characterization and first experiments

## Slide 18: Concepts equivalence
Definition (Instance-based equivalence)
  Two concepts are deemed to be equivalent if they are associated with, or classify the same set of objects
Definition (Schema-based equivalence)
  Two concepts are deemed to be equivalent if there exists a similarity among their features

## Slide 19: Concept equivalence in PMKI
Concepts alignment between semantic resources where only schema information is available
Schema-based equivalence
  Measurement of the conceptual/semantic similarity between concepts in given and target semantic resource

## Slide 20: Semantic Alignment formal characterization
Semantic Alignment (SA) characterized as a problem of Information Retrieval (IR)
  IR: retrieve documents, in a document collection, better matching the semantics of a query
  SA: retrieve concepts, in a target resource, better matching the semantics of a concept in a given resource
  SA ≡ IR
  Concept in given semantic resource Query
  Concept in target semantic resource Document

## Slide 21: Semantic Alignment formal characterization

## Slide 22: Logical views of concepts in source (Q) and target (D)thesauri
IR
  Query/Document represented by a term vector d of binary or weighted entries able to describe a semantic context
SA
  Thesaural concept represented by a term vector d of binary entries composed by
    the term itself
    relevant terms in its definition and in the alternative labels
    terms of directly related thesaural concepts (broader, narrower, related concepts)
  able to describe a semantic context

## Slide 23: Thesaural concept semantics
Vector d = [x1, . . . , x|T|], xi ∈ {0, 1} composed by
  the term itself
  relevant terms in its definition and in the alternative labels
  related thesaural concept terms
  T : dimension of the target thesaurus vocabulary
  xi : presence/absence of the ith vocabulary term in the concept d.
Pre-processing
  word stemming
  stopwords elimination

## Slide 24: Semantic interoperability in PMKI
Source Thesaurus
(Ex: Eurovoc)
Target Thesaurus
(Ex: Eclas)
Similarity
w1
w2
w3
w1
w5
w3
q = [w1, . . . , w|T|], xi ∈ {0, 1}
q
d

## Slide 25: The proposed Ranking Function (R)
Thesaural concepts similarity is measured as correlation between the related vectors
R = sim(q, d) =q×d/|q|·|d|
|q| and |d| are the norms of the vectors representing concepts in source and target thesauri.
  if sim(qi,dj ) < T1 ⇒ No Match
  if T1< sim(qi,dj)<T2 ⇒ Partial match (broad or narrowMatch)
  if T2 < sim(qi,dj ) ⇒ ExactMatch

## Slide 26: Criteria to create a Gold Standard
Exact Mapping
  A source concept corresponds exactly to one or more target concepts according to the expert judgment
Complete Mapping
  All source concepts are mapped to at least one broader and one narrower target concept
Complete and Optimal Mapping
  For each broad/narrow match the narrowest/broadest (the more/less specific) of all the broad/narrow matches is chosen

## Slide 27: Aligned datasets and first results
Semantic Alignments (Accuracy)
  ~89% EuroVoc and Eclas (European Commission Central Library thesaurus)
  ~92% Eurovoc and STW (Thesaurus of the German National Library of Economics)
  ~79% Eurovoc and TESEO (Italian Senate thesaurus)
Lexical vs. Semantic Resources (Accuracy)
  ~86% Eurovoc and IATE (European Parliament)
  … Eurovoc and WordNet
Notes: T = True
P = Positive
F = False
N = Negative
Precision: correct predictions over the retrieved TP / (TP + FN)
Recall: retrieved over all the expected TP / (TP + FP)
Accuracy: correct predictions over all the predictions (TP + TN) / (TP + TN + FP + FN)

## Slide 28: Example 1 of alignment
Properties | Concept 1 (EuroVoc) | Concept 2 (Eclas) | Similarity measure
Identifier: uri | http://eurovoc.europa.eu/3299 | http://ec.europa.eu/eclas/euc11/000000848 | 0.47
Label (preflabel) | "single market"@en | "EU/EC Single Market"@en | 
Alternative Label (altlabel) | "Community internal market"@en "EC internal market"@en "EU single market"@en | "European internal market"@en | 
definition | "Refers to the EU as one territory without any internal borders or other regulatory obstacles to the free movement of goods and services as defined by the Treaty on the Functioning of the European Union."@en |  | 
Remark (scopeNote) | "Do not confuse with EU market."@en |  | 

## Slide 29: Example 2 of alignment
Properties | Concept 1 (EuroVoc) | Concept 2 (Eclas) | Similarity measure
Identifier: uri | http://eurovoc.europa.eu/447 | http://ec.europa.eu/eclas/euc11/000001623 | 0.31
Label (preflabel) | "board of management"@en | "Executive management"@en | 
Alternative Label (altlabel) | "company management"@en "management team"@en |  | 
definition | "Committee of managers responsible for managing the company and answerable to the board."@en |  | 
Remark (scopeNote) |  |  | 

## Slide 30: Conclusions
PMKI is an ongoing project within ISA2
  Data model and technical architecture
  Results of automated alignments (next step: machine learning)
  Communication plan (conferences and workshops)
  Collaborations with external stakeholders (Language technology industry, Member States)
Final expected services
  Back-end platform for managing language resources and mappings
  Dissemination platform of Linked Open Data (SPARQL end point and RESTful API)

## Slide 31: Thank you for your attention Questions?
?

## Slide 32
ISA² programme
You click, we link.
Stay in touch
ec.europa.eu/isa2
@EU_isa2 isa@ec.europa.eu
Run by the Interoperability Unit at DIGIT (European Commission) with 131€M budget, the ISA2 programme provides public administrations, businesses and citizens with specifications and standards, software and services to reduce administrative burdens.

## Slide 33: Annexes

## Slide 34: Gold Standard
Thesauri | Couples of matching concepts
EUROVOC-ECLAS | 4099
EUROVOC-STW | 2959

## Slide 35: Experimental Results
Similarity Threshold | Eurovoc - Eclas |  |  |  | Eurovoc - STW |  |  | 
 | P | R | F | A | P | R | F | A
0.60 | 98.89 | 64.41 | 80.17 | 82.70 | 99.50 | 52.91 | 69.09 | 75.87
0.50 | 98.32 | 77.24 | 86.51 | 87.50 | 98.46 | 72.21 | 83.32 | 85.26
0.40 | 90.43 | 87.16 | 88.77 | 88.55 | 94.29 | 85.54 | 89.70 | 89.99
0.30 | 88.36 | 90.73 | 89.53 | 88.99 | 91.45 | 92.30 | 91.88 | 91.68
0.20 | 86.53 | 92.47 | 89.40 | 88.63 | 88.02 | 96.02 | 91.84 | 91.31

## Slide 36: Example 3 of alignment
Properties | Concept 1 (EuroVoc) | Concept 2 (Eclas) | Similarity measure
Identifier: uri | http://eurovoc.europa.eu/1161 | http://ec.europa.eu/eclas/euc11/000002579 | 0.0
Label (preflabel) | "logistics"@en | "Equipment management"@en | 
Alternative Label (altlabel) |  |  | 
definition |  |  | 
Remark (scopeNote) |  |  | 

## Slide 37: Example 4 of alignment
Properties | Concept 1 (EuroVoc) | Concept 2 (Eclas) | Similarity measure
Identifier: uri | http://eurovoc.europa.eu/1670 | http://ec.europa.eu/eclas/euc11/000003184 | 0.23
Label (preflabel) | "linguistics"@en | "Linguistics"@en | 
Alternative Label (altlabel) | "grammar"@en "lexicology"@en "phonetics"@en "pronunciation"@en "semantics"@en "etymology"@en "spelling"@en | "Language study"@en | 
definition |  |  | 
Remark (scopeNote) |  |  | 

## Slide 38: Example 5 of alignment
Properties | Concept 1 (EuroVoc) | Concept 2 (Eclas) | Similarity measure
Identifier: uri | http://eurovoc.europa.eu/3165 | http://ec.europa.eu/eclas/euc11/000005201 | 0.49
Label (preflabel) | "market stabilisation"@en | "Market stabilization"@en | 
Alternative Label (altlabel) | "improvement of market conditions"@en "market regularisation"@en "market regularization"@en "market stabilization"@en "stabilisation of prices"@en "stabilization of prices"@en | "Language study"@en | 
definition |  |  | 
Remark (scopeNote) |  |  | 

## Slide 39: Example 6 of alignment
Properties | Concept 1 (EuroVoc) | Concept 2 (Eclas) | Similarity measure
Identifier: uri | http://eurovoc.europa.eu/2599 | http://ec.europa.eu/eclas/euc11/000004299 | 0.70
Label (preflabel) | "press"@en | "Press"@en | 
Alternative Label (altlabel) | "journalism"@en |  | 
definition |  |  | 
Remark (scopeNote) |  |  |